Paid Media Campaign Status Report

Mortgage ABM — Case Study Campaigns

Thursday, February 19, 2026

Executive Summary We are running mortgage ABM case study campaigns across three platforms: LinkedIn, Meta (Facebook/Instagram), and Google Ads. LinkedIn is the only platform actively delivering. The Meta campaigns are built but still in draft and need to be published. The Google Ads YouTube pre-roll campaign is enabled but the audience list is under review by Google, so no impressions have been served yet. Total combined daily budget once all platforms are live: $349/day (~$10,470/month).

| $349 Total Daily Budget across 3 platforms | $376.52 Active Spend LinkedIn only | 12,348 Total Impressions LinkedIn only | 171 Total Clicks 1.39% blended CTR |
| --- | --- | --- | --- |

Cross-Platform Overview

| Platform | Campaigns | Daily Budget | Spend | Impressions | Status |
| --- | --- | --- | --- | --- | --- |
| LinkedIn | 3 | $200/day | $376.52 | 12,348 | ● Live |
| Meta / Facebook | 3 (1 parent) | $99/day | $0 | 0 | ● Draft |
| Google Ads | 1 active | $50/day | $0 | 0 | ● Under Review |

LinkedIn Campaign Manager

Account: Truv Ad Account (ID: 517969837)

Objective: Website Visits  |  Optimization: Landing Page Clicks (Maximum Delivery)

Audience: Contact List “Top 250: mortgage-ops-targets” (~610 members)

Segments: Operations 38%, Finance 18%, Business Development 15%, Sales 8%

| Campaign | Budget | Ads | Spend | Impressions | Clicks | CTR |
| --- | --- | --- | --- | --- | --- | --- |
| CCM Case Study – Ops Audience | $50/day | 4 | $26.13 | 238 | 0 | 0% |
| FCM Case Study – Ops Audience | $50/day | 4 | $29.22 | 133 | 5 | 3.76% |
| PHM Case Study – Ops Audience | $100/day | 9 | $321.17 | 11,977 | 166 | 1.39% |

Key observations: FCM has the highest CTR at 3.76%, despite the smallest impression volume. PHM dominates total volume with $321 in spend and 12K impressions, driven by its doubled budget ($100/day) and 9-ad creative rotation. CCM has generated 238 impressions but no clicks yet—worth monitoring creative resonance.

Meta / Facebook Ads

Account: Truv B2B (ID: 1048327588356046)

Campaign: Truv | Mortgage ABM | Case Studies | Feb 2026

Objective: Awareness (Maximize Reach)  |  Campaign Score: 67/100

Audience: Custom List “truvOPs-meta-custom-audience” (High Value) — Est. 2,000–2,300 people

Targeting: United States, Ages 18–65+, All Genders, All Languages

Frequency Cap: 2 impressions every 2 days

| Ad Set | Daily Budget | Creative | Status |
| --- | --- | --- | --- |
| First Continental Mortgage | $33/day | Static ¦ Cost Savings (1 ad) | ● Draft |
| CrossCountry Mortgage | $33/day | Static ¦ Cost Savings (1 ad) | ● Draft |
| Prosperity Home Mortgage | $33/day | Static ¦ Cost Savings (1 ad) | ● Draft |

Action required: All three ad sets are toggled on but remain in draft status. There are 7 items in the “Review and publish” queue in Ads Manager. These campaigns will not spend until they are published.

Google Ads

Account: Truv (cameron.wolf@truv.com)

Total campaigns in account: 30 (28 paused, 2 ended, 1 active)

Active Campaign: CCM Case Study – YouTube Pre-Roll – Feb 2026 Type: Demand Gen ¦ Goal: Clicks ¦ Budget: $50/day Channels: YouTube In-Stream, YouTube In-Feed, Gmail Audience: “CCM Customer Match – Mortgage ABM” with segment “Google Expansion – Mortgage Ops Leaders – Feb 2026” Creative: 4 CrossCountry Mortgage case study videos (0:40–1:10) Destination: truv.com/lp/crosscountry-mortgage-case-study Status: Bid strategy learning. Audience list currently under review by Google. No impressions served yet. Ad strength flagged as Incomplete.

The remaining 29 paused/ended campaigns are legacy Search, Display, and Performance Max campaigns from earlier initiatives. All show $0 spend in the last 30 days.

Action Items

- Publish Meta campaigns: Review the 7 pending items in Ads Manager and publish all three ad sets (FCM, CCM, PHM) to begin delivery.

- Monitor Google audience review: The Customer Match list is under review. Once approved, the YouTube pre-roll campaign should start delivering. Also address the “Ad strength: Incomplete” flag by adding headlines/descriptions.

- Watch CCM LinkedIn performance: 238 impressions with 0 clicks. If this continues, consider refreshing creative or ad copy for this campaign.

- Review PHM budget allocation: PHM is set at $100/day (double the others). Confirm this is intentional given it’s capturing the majority of spend and impressions.

Prepared by Cameron Wolf, Sr. Marketing Manager

Data pulled from LinkedIn Campaign Manager, Meta Ads Manager, and Google Ads on Thursday, February 19, 2026.